## Sheet
﻿id | title | start | end | owner | duration_weeks
1 | Requirements collection and prioritization | 2026-02-12 | 2026-02-26 | PM | 2
2 | Architecture draft (data/API/DB) | 2026-02-26 | 2026-03-09 | Tech Lead | 1.5
3 | Scraper PoC (Playwright + BS4) | 2026-03-02 | 2026-03-16 | Dev Team | 2
4 | Markdown conversion pipeline | 2026-03-09 | 2026-03-30 | Dev Team | 3
5 | DeepSeek integration tests | 2026-03-23 | 2026-04-06 | AI Engineer | 2
6 | API/Backend implementation (FastAPI) | 2026-04-16 | 2026-05-06 | Dev Team | 3
7 | Frontend prototype (Streamlit) | 2026-04-16 | 2026-04-30 | Frontend | 2
8 | Deployment automation | 2026-05-07 | 2026-05-20 | DevOps | 2
9 | Internal QA and pilot deploy | 2026-05-21 | 2026-05-30 | QA/PM | 1